## 0 Cover Sheet
Monthly Job Review Packet — Cover Sheet
Firm Name | «Firm Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
Jobs Included (Packet Index)
Job # | Job Name | PM | Contract Type | Forecast GP % | Over/(Under) Billed | COs Outstanding (Unapproved) | AR/Retainage Notes
Portfolio Snapshot (This Month)
# Active jobs reviewed |  |  | «#»
Jobs with margin fade this month |  |  | «#»
Top 3 risk jobs (by $ exposure) |  |  | «Job / Job / Job»
Top 3 cash constraints |  |  | «e.g., underbilling, disputed AR, retainage concentration»
This Month’s Key Decisions
Decision |  |  |  | Impacted Job(s) |  | Owner | Due Date | Status
Follow-ups Carried Forward (From Prior Month)
Job |  |  | Follow-up Item |  |  | Owner | Due Date | Status
Packet Complete Checklist (Per Job)
Summary Sheet included and updated | [8 empty] | ☐
Contract Extract on file (or updated if terms changed) | [8 empty] | ☐
Job Cost Review updated with current EAC assumptions | [8 empty] | ☐
Change Order Log updated with status + next action owner | [8 empty] | ☐
Billing status reviewed (over/under billings and retainage) | [8 empty] | ☐
AR/disputes noted (if applicable) | [8 empty] | ☐

## A Summary Sheet
Monthly Job Review Packet
Firm Name | «Firm Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
Template A: Summary Sheet (1 page)
Use this as the one-page snapshot for each active job. Keep format consistent across PMs.
Job name / number |  |  | Owner / Project type
PM / Superintendent |  |  | Start / Est. finish |  | To
Contract type |  |  | Original contract
Approved change orders |  |  | Revised contract
Cost to date |  |  | Forecast EAC
Forecast GP$ / GP% |  |  | % complete (basis) |  | (cost / production)
Over/under billings |  |  | Retainage
Drivers of change this month (bullets)
1) |  | 2) |  | 3)
Top 3 risks / Top 3 actions
Risks |  |  | Actions

## B Contract Extract
Monthly Job Review Packet
Firm Name | «Firm Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
Template B: Contract Extract (profit/cash terms)
Summarize key terms that impact billing, cash, profit, and risk. Create once and carry forward.
Billing terms |  | Retainage %
Pay app cutoff / due date |  | Notice requirements
LDs / bonuses |  | Allowances / contingency rules
Change order procedure |  | Claims / ADR
Insurance / indemnity triggers |  | Key milestones

## C Job Cost Review
Monthly Job Review Packet
Firm Name | «Firm Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
Template C: Job Cost Review (variance + forecast)
Summarize budget vs. actual vs. forecast by major cost codes. Drill down only for variances.
Cost code | Budget | Cost to date | Committed | Cost to complete | EAC | Variance | PM note (1–2 lines)
Labor
Materials
Equipment
Subcontracts
Other
TOTAL | 0 | 0 | 0 | 0 | 0 | 0

## D Change Order Log
Monthly Job Review Packet
Firm Name | «Firm Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
Template D: Change Order Log (pipeline + collection)
Track each change from identification through approval, billing, and collection. Assign next actions and owners.
CO # | Description | Amount | Status | Aging (days) | Next action + owner | Billed | Collected
Implementation note: Speed and consistency beat perfection. Start with consistent inputs (cost coding, commitments maintenance, and timely job cost posting).

## E GC Commitments
GC Add-On — Commitments & Exposure Summary
Company | «Company Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
How to use
Use this page to ground your forecast in committed costs. Update executed subcontracts and POs, identify scope gaps and pending changes, and focus discussion on the largest exposure items.
Commitments & Exposure (by major trade / cost code)
Trade / Cost Code | Scope / Notes | Budget | Committed (Executed) | Pending Change Commitments | Forecast Cost-to-Complete (CTC) | EAC (Forecast Total Cost) | Exposure / Variance (Budget - EAC) | Owner / Next Action | Target Date
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0

## F Sub Productivity
Subcontractor Add-On — Labor Productivity & Earned Hours Tracker
Company | «Company Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
How to use
Use this page to monitor labor productivity. Enter budget hours, the best available measure of progress (% complete or quantities installed), and actual hours to date. Review the variance and update forecast hours-to-complete each month (or weekly on key jobs).
Labor Productivity (by phase / cost code)
Phase / Cost Code | Work Description / Notes | Budget Hours | % Complete (or Progress) | Earned Hours | Actual Hours to Date | Variance (Earned - Actual) | Forecast Hours to Complete | Key Driver / Constraint | Target Date
TOTAL |  | 0 |  | 0 | 0 | 0 | 0

## G AR Retainage
Add-On — Job-Level AR & Retainage Detail
Company | «Company Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
How to use
Use this page to identify cash risk by job. Break open receivables into aging buckets, track retainage, and assign next actions for disputes or slow-paying customers. Review trends month over month.
AR & Retainage Summary (by job)
Job # | Job Name / Customer | Billing to Date | Open AR — Current | Open AR — 1–30 | Open AR — 31–60 | Open AR — 61–90 | Open AR — 90+ | Retainage Outstanding | Next Action / Owner
TOTAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash Risk Flags (check if applicable)
AR balance includes disputed amounts (document dispute and resolution plan). | [8 empty] | ☐
Retainage is concentrated or materially overdue (confirm requirements for release). | [8 empty] | ☐
Billing is behind progress (identify blocker: COs, schedule of values, owner approvals). | [8 empty] | ☐
Customer has slow-pay history (escalate and tighten billing/collection cadence). | [8 empty] | ☐

## H Job Health
Add-On — Job Health Scorecard (Green / Yellow / Red)
Company | «Company Name»
Reporting Month | «Month YYYY»
Job Name / Job # | «Job Name / #»
Prepared By / Date | «Name – mm/dd/yyyy»
How to use
Use this scorecard to focus leadership time. For each job, rate a small set of risk indicators as Green, Yellow, or Red and document the single most important action to stabilize the job. Keep the criteria consistent month to month.
Criteria (edit as needed)
Default criteria: | Edit the list below if your team uses different risk scans.
• Margin trend vs prior month
• Forecast confidence (assumptions supported)
• Billing position (over/under billings)
• Change order recovery (aging/unbilled)
• Schedule risk / recovery plan
• Labor productivity (earned vs actual)
• Cash risk (AR aging / disputes / retainage)
• Quality / rework / punch list risk
Job Health Scorecard
Job # | Job Name | Overall | Margin | Forecast | Billing | COs | Schedule | Top Risk / Next Action | Owner / Due Date
Tip: Keep 'Overall' conservative. If any one category is Red, the job is usually at least Yellow overall.